RUN OF SHOW

Event  ________________________    Date  ____________    Venue  ________________________

Day-of contact  ________________________    Phone  ____________    Version  ____

Schedule (sample wedding day, change every time to yours)

| # | Time | What happens | Owner | Cues and notes |
| --- | --- | --- | --- | --- |
| 1 | 3:30 PM to 4:00 PM 30 min | Guests arrive and are seated Ceremony lawn | Coordinator | Prelude music at 3:45. Ushers in place by 3:15. |
| 2 | 4:00 PM to 4:25 PM 25 min | Ceremony Ceremony lawn | Coordinator | Processional on the coordinator’s signal; officiant mic live. Allow 10 minutes of slack in case the start runs late. |
| 3 | 4:25 PM to 5:25 PM 60 min | Cocktail hour Terrace | Caterer | Bar open, appetizers out before guests walk in. Guests directed from the ceremony by ushers. |
| 4 | 4:25 PM to 5:15 PM 50 min | Family and couple photos Garden | Photographer | Family list read by a named helper. Shot list given to the photographer a week ahead. |
| 5 | 5:25 PM to 5:40 PM 15 min | Guests to the reception room, grand entrance Reception room | Coordinator | Entrance song cued; DJ announces. Doors stay closed until the room is ready. |
| 6 | 5:40 PM to 5:50 PM 10 min | First dance Dance floor | DJ or band | Song cued, dance floor lights set. Photographer in position before the song starts. |
| 7 | 5:50 PM to 6:50 PM 60 min | Dinner served Reception room | Caterer | Kitchen fires on the coordinator’s word. Dietary meals served first, by seat. |
| 8 | 6:50 PM to 7:10 PM 20 min | Toasts Head table | Coordinator | Handheld mic tested at 5:00; music down. Three speakers, three minutes each. |
| 9 | 7:10 PM to 7:25 PM 15 min | Cake cutting Cake table | Coordinator | Cake table lit; song cued. Cake knife and plates ready. |
| 10 | 7:30 PM to 10:30 PM 180 min | Open dancing Dance floor | DJ or band | Last call announced at 10:15. Music ends at 10:30, per the contract. |
| 11 | 10:30 PM to 10:45 PM 15 min | Last dance and send-off Front drive | DJ or band | Last song cued; lights up at 10:45. Sparklers or bubbles staged outside by 10:20. |
| 12 | 10:45 PM to 11:00 PM 15 min | Venue clear, lights up Whole venue | Venue | House lights up. Vendors out by 11:30. Walk the room with the couple’s family. |

Vendor contacts

| Role | Name | Phone | Arrives |
| --- | --- | --- | --- |
| Coordinator |  |  |  |
| Caterer |  |  |  |
| Photographer |  |  |  |
| DJ or band |  |  |  |
| Florist |  |  |  |
| Venue manager |  |  |  |

Rain plan

Outdoor blocks move to  ________________________.  Decision made by  ____________  at  ________.

Send every vendor the latest version, numbered, after each change.

A sample wedding run of show from myvenuehq.com/blog/wedding-run-of-show-template. Build your own with the free run of show template at myvenuehq.com/free-run-of-show-template